# Riverside Water Reclamation — Phase 2 Expansion

Project ID: NW-WW-2103 Status at archive: Closed, handed over Q4 last fiscal year, 7 months into warranty. Contract value: $42 million, fixed-price. Duration: 22 months from Award to Substantial Completion. Substantial Completion delivered 6 weeks late. Final margin: 4.1% (against bid margin of 8.5%).

## What the project did

Capacity expansion of the Riverside Municipal Water Reclamation Facility — a wastewater treatment plant serving a city of ~180,000 — from 18 MGD to 30 MGD treatment capacity, with associated headworks, biological treatment trains, secondary clarifiers, and tertiary filtration upgrades.

## Why margin compressed

Two main causes. A 14-week delay in delivery of two large blowers from a single-sourced European vendor, which absorbed almost all the project’s contingency. And a late client-driven change order (Q2 of construction) adding UV disinfection capacity that was negotiated at thin margin. Liquidated damages were assessed for the late completion but were partially offset by a successful claim for client-driven scope additions.

## Outcomes

- Performance tests passed first attempt.

- Client relationship intact; Northwood was shortlisted for the Phase 3 work.

- Lessons-learned write-up flagged single-sourced critical equipment as a category-level risk for the firm.