# Project Charter — Riverside Water Reclamation Phase 2 Expansion

## 1. Project identification

- Project name: Riverside Water Reclamation — Phase 2 Expansion

- Project ID: NW-WW-2103

- Client: City of Riverside Public Works Department

- Contract type: Fixed-price

- Contract value: $42.0 million

- Effective date: 12 March

- Target substantial completion date: 30 January, year+2

- Sponsor (Northwood): VP Water & Wastewater

- Project Director: R. Tannehill

- Project Manager: M. Acharya

## 2. Overview

Expansion of the City of Riverside’s existing 18 MGD wastewater treatment facility to a treated capacity of 30 MGD. Northwood will design, procure, build and commission additional headworks screening, two new biological treatment trains, two secondary clarifiers, tertiary filtration improvements, and the associated electrical, instrumentation and control systems. Project enables the city to meet projected demand through year+15 and to satisfy a state-mandated effluent standard taking effect in three years.

## 3. Objectives

- Deliver treated capacity of 30 MGD, verified through 30-day continuous performance test, by 30 January year+2.

- Achieve effluent compliance with the new state standard (TN <8 mg/L, TP <0.5 mg/L) verified during the performance test.

- Maintain plant operations throughout construction with no unplanned process upsets exceeding state-permit thresholds.

- Deliver the project at or above 8.5% margin on contract value, with cost variance within ±3% of approved budget.

- Achieve zero lost-time injuries across the construction period.

## 4. Scope

### 4.1 In scope

- Detailed design of all civil, mechanical, electrical and I&C work packages.

- Procurement of all process equipment, including aeration blowers, clarifier mechanisms, filtration media, and SCADA upgrades.

- Construction of two new biological treatment basins, two new secondary clarifiers, headworks expansion, and tertiary filter retrofit.

- Tie-ins to existing process trains during scheduled plant shutdowns.

- Commissioning, performance testing, operator training, and as-built documentation.

- 24-month warranty period.

### 4.2 Out of scope

- Sludge dewatering capacity expansion (client deferred to a future phase).

- Effluent outfall modifications (separate contract awarded to a marine specialist).

- Headworks grit removal equipment replacement (client-supplied, installed by client’s O&M team).

- Plant administration building improvements.

## 5. Key stakeholders

| Role | Name | Organisation | Responsibility |
| --- | --- | --- | --- |
| Sponsor | VP Water & Wastewater | Northwood | Internal accountability, monthly reviews |
| Project Director | R. Tannehill | Northwood | Commercial outcome, escalations |
| PM | M. Acharya | Northwood | Day-to-day delivery |
| Client Project Manager | D. Hoffmann | City of Riverside | Single point of contact on client side |
| Plant Superintendent | K. Velasquez | City of Riverside | Operations interface during construction |
| State Regulator | (Various) | State Environmental Agency | Permits, inspections, performance test sign-off |

## 6. Schedule and milestones

| Milestone | Target date | Payment milestone? |
| --- | --- | --- |
| Detailed Engineering 60% review | 30 August | Yes |
| Long-lead equipment POs released | 15 October | No |
| Mobilisation on site | 20 January, year+1 | Yes |
| First new biological train commissioned | 30 September, year+1 | Yes |
| Second train commissioned, tie-ins complete | 30 November, year+1 | Yes |
| Performance test commenced | 1 December, year+1 | No |
| Substantial Completion | 30 January, year+2 | Yes |

## 7. Commercial baseline

- Contract value: $42.0 million

- Internal target margin: 8.5%

- Approved budget (cost): $38.4 million

- Contingency (Northwood): $1.8 million

- Liquidated damages exposure: 0.4% of contract value per week, capped at 8% ($3.36 million)

- Retention terms: 10% retention; 50% released at Substantial Completion, 50% at end of warranty

- Payment terms: Net 30 from approved invoice; milestone-based

## 8. Risks (top 5)

| Risk | Category | Probability | Impact | Response |
| --- | --- | --- | --- | --- |
| Long-lead blower delivery exceeds 32 weeks | Schedule | M | H | Mitigate — early PO release, expediting, secondary supplier qualified |
| Client-driven scope change for additional UV disinfection capacity | Commercial | M | M | Transfer — formal change order required; pricing pre-agreed in master agreement |
| Process tie-ins exceed permitted plant shutdown windows | Schedule | M | H | Mitigate — detailed sequencing plan, dry runs, weekly coordination with plant superintendent |
| Effluent performance test fails on TN limit | Technical | L | H | Mitigate — design margin on biological reactor sizing, third-party process validation review |
| Sub-contractor on civil works fails to perform | People | L | H | Mitigate — prequalified contractor, performance bond, monthly cash-flow tracking |

## 9. Assumptions

- Existing plant remains in continuous operation throughout construction.

- Permitted shutdown windows align with seasonal flow patterns as historically observed.

- Client-supplied grit removal equipment is delivered to site no later than 30 June year+1.

- State regulator’s performance test procedure remains as agreed in proposal.

## 10. Constraints

- Plant must maintain effluent compliance throughout construction.

- Construction noise limited to daytime hours by city ordinance.

- State-mandated effluent standard takes effect on 30 March year+2 — no schedule slip possible past this date without permit consequence.

## 11. Governance

- Reporting cadence: weekly internal status, monthly client status, monthly Northwood portfolio dashboard.

- Decision rights: PM up to $50k variation; Director up to $500k; Sponsor above.

- Change-order thresholds: all client-driven changes through formal change-order process; internal-only changes documented in PM log.

- Escalation path: PM → Director → Sponsor → CFO (only if value impact > $1M).

## 12. Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Sponsor | VP Water & Wastewater | (signed) | 8 March |
| Project Director | R. Tannehill | (signed) | 8 March |
| Project Manager | M. Acharya | (signed) | 10 March |