# Weekly Status — Riverside Water Reclamation Phase 2 Expansion

Project: NW-WW-2103 Riverside Water Reclamation Phase 2 Expansion Reporting period: Week 36 of construction (ending Sunday) PM: M. Acharya Status (overall): Amber — Blower delivery slip threatens commissioning sequence

## Headline

Confirmed 8-week delay on Train B blower shipment from the European OEM (now expected dock 22 November, was 27 September). This consumes the remaining schedule contingency on the commissioning sequence and creates a hard conflict with the December performance test window. Mitigation in progress; Sponsor decision needed by 30 October on whether to commit to a Plan B partial commissioning sequence.

## Progress

- Engineering: 98% complete. Final close-out drawings for Train B controls in review.

- Procurement: Train A blower delivered to site 12 September; uncrated, no damage. Train B blower delay confirmed by OEM.

- Construction: Train A basin civil works 100%; M&E install 88%. Train B basin civil works 100%; M&E install 64%. Tertiary filter retrofit 78%.

- Commissioning / handover: N/A (commissioning starts post 30 September).

## Schedule

- Variance to plan: -3 weeks against current baseline (after this week’s blower slip).

- Critical path: Train B commissioning. No float remaining.

- Forecast completion: 6–8 weeks late if Plan A commissioning sequence is maintained; 0–2 weeks late if Plan B (Train A early commissioning, Train B sequenced after) is approved.

## Cost and commercial

- Cost-to-date vs plan: -$420k (under spend, primarily due to deferred Train B blower payment).

- Forecast cost at completion vs budget: +$680k (overrun, driven by expediting costs and overtime).

- Margin trajectory: dropping from 8.5% bid to a forecast 5.2%.

- Active change orders: CO-04 (additional UV disinfection capacity, $1.85M, client-approved); CO-07 (revised SCADA scope, $115k, in negotiation).

- Claims exposure: none active. Considering letter of intent on schedule impact tied to client-driven CO-04.

## Risks and issues

- Escalated: R-001 (long-lead blower delivery) now Triggered. Plan B commissioning sequence being prepared.

- New: R-014 — Risk that performance test cannot start until 15 January year+2 (vs planned 1 December year+1). Impacts state-mandated effluent compliance date.

- Decision needed: Sponsor to approve or reject Plan B commissioning sequence by 30 October. Plan B option document attached to this report.

## Safety / quality / environment

- Zero LTIs to date. One first-aid case (minor cut, ground crew) this week.

- NCR-12 (tertiary filter media — out-of-spec batch) closed; replacement media on site, installation this week.

- No environmental incidents.

## Look-ahead (next two weeks)

- Train A mechanical completion (target 30 September).

- Plan B sequencing document to Sponsor by 25 October.

- Client coordination meeting on commissioning schedule, 28 October.

- State regulator pre-test walkthrough, 14 November.

## Asks

- Sponsor decision on Plan B commissioning sequence, by 30 October. Owner: VP Water & Wastewater.

- Director approval for $115k CO-07 internal cost release pending client signature. Owner: R. Tannehill.

- Procurement support to expedite Train B blower at OEM factory. Owner: Procurement Manager.