# Weekly Status — Riverside Water Reclamation Phase 2 Expansion

Project: NW-WW-2103 Riverside Water Reclamation Phase 2 Expansion Reporting period: Week 72 of construction (ending Sunday) PM: M. Acharya Status (overall): Green — Performance test passed first attempt

## Headline

30-day continuous performance test completed successfully on Tuesday. All effluent parameters within state-permit limits including the new TN and TP thresholds. State regulator signed off on Wednesday. Substantial Completion certificate executed Thursday. Project moves into 24-month warranty period.

## Progress

- Engineering: 100% complete; as-built drawings issued to client.

- Procurement: all equipment closed out, vendor warranties registered.

- Construction: 100% complete; punch list closed Friday.

- Commissioning / handover: Substantial Completion achieved 6 weeks behind original baseline, 0 weeks behind Plan B baseline.

## Schedule

- Variance to plan: -6 weeks against original baseline; 0 weeks against approved Plan B baseline.

- Critical path: N/A (project complete).

- Forecast completion: Substantial Completion 12 March year+2 (delivered 11 March).

## Cost and commercial

- Cost-to-date vs plan: +$1.4M overrun against original budget; +$0.2M against revised budget (post change orders).

- Forecast cost at completion vs budget: Final cost confirmed at $40.3M against budget $38.4M.

- Margin trajectory: Final margin 4.1% (against bid 8.5%).

- Active change orders: all closed. Final value: +$2.1M added to contract scope.

- Liquidated damages: $560k assessed (6 weeks × 0.4% × $42M, partially recovered through client-driven CO claim).

- Claims: Schedule-impact claim against CO-04 settled at $340k recovered.

## Risks and issues

- All open risks closed at handover.

- Lessons-learned write-up issued separately. Headline lesson: single-sourced critical-path equipment is a category-level risk requiring portfolio-level supplier diversification.

## Safety / quality / environment

- Zero LTIs across the entire project. 4 first-aid cases over 18 months on site. Zero environmental incidents. Two NCRs raised, both closed within 30 days.

## Look-ahead (next two weeks)

- Final invoice submission to client, 18 March.

- 50% retention release expected, 30 April.

- Project closeout review with Sponsor, 25 March.

- Warranty period commences immediately. Quarterly check-ins scheduled.

## Asks

- Sponsor approval to release project team back to portfolio, effective 30 March. Owner: VP Water & Wastewater.

- Director to chair closeout review and lessons-learned session, 25 March. Owner: R. Tannehill.