# Risk Register — Riverside Water Reclamation Phase 2 Expansion

Project ID: NW-WW-2103 Status snapshot: End of project (handover + 1 month). All risks closed.

| ID | Category | Description | Probability | Impact | Score | Response | Owner | Trigger | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-001 | Schedule | Long-lead blower delivery from sole European OEM may exceed 32 weeks, leading to commissioning slip. | M | H | 6 | Mitigate — early PO release, weekly expediting, secondary OEM qualification | Procurement Manager | OEM confirms shipment delay > 4 weeks at any milestone review | Closed (Triggered Wk 35; Plan B commissioning sequence approved Wk 36) |
| R-002 | Commercial | Client may issue late scope change for UV disinfection capacity, eroding margin if priced thin. | M | M | 4 | Transfer — formal change-order with pre-agreed unit rates in master agreement | Project Manager | Client raises UV requirement in design review | Closed (CO-04 executed Wk 14, $1.85M added at 6% margin) |
| R-003 | Schedule | Plant shutdown windows for tie-ins may exceed permitted hours, breaching consent. | M | H | 6 | Mitigate — detailed sequencing, dry runs, plant-superintendent weekly coordination | Construction Manager | Any tie-in projected to exceed 36-hour shutdown window | Closed (4 tie-ins executed; longest 30 hours) |
| R-004 | Technical | Effluent performance test may fail on TN limit if biological reactor sizing too conservative. | L | H | 3 | Mitigate — design margin on basin volume, third-party process validation review pre-construction | Process Engineering Lead | TN trending > 7 mg/L during pre-test runs | Closed (test passed first attempt) |
| R-005 | People | Civil sub-contractor may fail to perform, given prior performance issues on a peer project. | L | H | 3 | Mitigate — prequalification, performance bond, monthly cash-flow tracking | Project Manager | Sub falls > 2 weeks behind committed schedule | Closed (sub performed adequately; one cash-flow intervention required) |
| R-006 | Regulatory | New state standard effective 30 March year+2 — no schedule slip possible past this date without permit consequence. | L | H | 3 | Avoid — Plan B sequencing locked to deliver before this date | Project Director | Forecast completion projects past 1 March year+2 | Closed (Substantial Completion 11 March year+2, before deadline) |
| R-007 | External | Client may reassign their PM during project, causing decision delays. | M | M | 4 | Accept — escalation path documented, weekly client check-in | Project Manager | Client PM out of role | Closed (no reassignment) |
| R-008 | Safety / HSE | Confined-space entry for tie-ins carries elevated incident risk. | L | H | 3 | Mitigate — written confined-space procedures, daily JSAs, dedicated safety stand-down before each tie-in | HSE Lead | Any near-miss reported during a tie-in | Closed (zero incidents) |
| R-009 | Technical | SCADA upgrade integration may introduce process upsets affecting effluent compliance. | M | M | 4 | Mitigate — staged commissioning, parallel running of old and new SCADA, rollback plan | I&C Lead | Any process variance > 10% on parallel-running data | Closed (no upsets; cutover successful) |
| R-010 | Commercial | Currency exposure on European blower POs (~$3.2M total). | M | M | 4 | Transfer — forward currency contract at PO release | Procurement Manager | EUR/USD moves > 5% between PO date and payment | Closed (forward contracts hedged exposure; no material variance) |

## Lessons logged from this register

- Single-sourced critical-path equipment is a category-level risk. R-001 alone consumed almost the entire project contingency. Northwood should require dual-source qualification for any critical-path equipment with lead time greater than 6 months.

- Plan B sequencing exercises before the schedule is in trouble. The Plan B commissioning sequence was conceived only after R-001 triggered. Future projects of similar scale should war-game alternative commissioning sequences during Engineering, not under pressure during Construction.

- Currency hedging is consistently profitable. Forward contracts on R-010 contributed positively to margin protection. Should be standard for any EUR/JPY exposure greater than $1M.