# Project Charter — Skyhawk Solar + Storage Phase 1

Note on this document’s role as a worked example. This is the FINAL committed charter for Skyhawk, signed at the Award gate. When the Charter Drafter agent uses this as a worked example for drafting a new project’s charter, the commercial-baseline values (§7), governance thresholds (§11), and other inferred industry-standard defaults should be flagged with [NEEDS PM REVIEW: <value>] at the draft stage, not committed as shown here. Inline annotations in italic below the relevant lines show the draft-stage form for each inferred value, so the desired pattern is visible. The final values shown are what the Skyhawk commercial team confirmed during the Award-gate review; a new project’s draft charter would have these in flagged form until the equivalent commercial confirmation.

## 1. Project identification

- Project name: Skyhawk Solar + Storage Phase 1

- Project ID: NW-REN-2207

- Client: Skyhawk Renewables LLC (IPP)

- Contract type: Fixed-price

- Contract value: $68.0 million

- Effective date: 5 April

- Target substantial completion date: 5 June, year+1

- Sponsor (Northwood): VP Renewables

- Project Director: L. Chen

- Project Manager: J. Okafor

## 2. Overview

EPC delivery of a 200 MW solar photovoltaic generation facility with a co-located 100 MWh / 4-hour lithium-iron-phosphate battery energy storage system in the desert southwest. Northwood designs, procures and constructs the PV array, BESS, substation, MV collection system, and 230 kV grid interconnection. Client operates under a 20-year power purchase agreement with the regional utility.

## 3. Objectives

- Deliver 200 MW DC nameplate solar generation, verified through commissioning power test, by 5 June year+1.

- Deliver 100 MWh BESS with ≥95% round-trip efficiency at commissioning, sustained.

- Achieve grid interconnection energisation by 1 May year+1 to enable 35-day commissioning window.

- Deliver at or above 8.8% margin with cost variance within ±2% of approved budget.

- Zero lost-time injuries across construction.

## 4. Scope

### 4.1 In scope

- Detailed design of PV, BESS, substation, MV collection, interconnection.

- Procurement of modules, inverters, BESS containers, transformer, switchgear, racking.

- Construction including grading, foundations, tracker installation, BESS pad, MV trenching, substation construction, fencing, access roads.

- Commissioning, performance testing, training, as-builts.

- 24-month warranty.

### 4.2 Out of scope

- Land acquisition (client).

- Environmental permitting (client; Northwood supports).

- 230 kV transmission line from substation to grid POI (separate utility-led contract).

- O&M services post handover.

## 5. Key stakeholders

| Role | Name | Organisation | Responsibility |
| --- | --- | --- | --- |
| Sponsor | VP Renewables | Northwood | Internal accountability |
| Project Director | L. Chen | Northwood | Commercial outcome |
| PM | J. Okafor | Northwood | Day-to-day delivery |
| Client Lead | R. Sutter | Skyhawk Renewables | Primary client interface |
| Utility Coordinator | (TBC) | Regional Utility | Interconnection studies, energisation |
| BESS OEM | (BESS vendor) | (BESS vendor) | Battery delivery, integration support, warranty |

## 6. Schedule and milestones

| Milestone | Target date | Payment milestone? |
| --- | --- | --- |
| Detailed Engineering 30% review | 30 June | Yes |
| Long-lead POs released (modules, inverters, BESS) | 15 August | No |
| Site mobilisation | 1 October | Yes |
| Mechanical completion — PV array | 15 March, year+1 | Yes |
| BESS commissioned | 30 April, year+1 | Yes |
| Grid interconnection energisation | 1 May, year+1 | Yes |
| Substantial Completion | 5 June, year+1 | Yes |

## 7. Commercial baseline

- Contract value: $68.0 million (from intake; no flag needed)

- Internal target margin: 8.8% (from intake; no flag needed)

- Approved budget (cost): $62.0 million (calculated as Contract value × (1 − margin); no flag needed because derivable)

- Contingency: $2.5 million (at draft stage this was [NEEDS PM REVIEW: industry-standard contingency for this project class]; commercial team confirmed $2.5M at Week 2 review)

- LDs: 0.5%/week capped at 10% ($6.8M) (at draft stage this was [NEEDS PM REVIEW: LD terms — confirm with commercial team]; agreed during contract negotiation)

- Retention: 7.5%, half released at SC, half at end of warranty (at draft stage this was [NEEDS PM REVIEW: retention terms]; standard Northwood EPC terms confirmed)

- Payment terms: Net 30, milestone-based (at draft stage this was [NEEDS PM REVIEW: payment terms]; client agreed at contract signature)

## 8. Risks (top 5)

| Risk | Category | Probability | Impact | Response |
| --- | --- | --- | --- | --- |
| Utility interconnection studies delivered late, delaying energisation | Regulatory | M | H | Mitigate — engage utility coordinator from Day 1, escalation path via PPA terms |
| BESS supply-chain disruption | Schedule | M | H | Mitigate — early PO, dual-source qualification, factory acceptance test |
| Module degradation higher tha |  |  |  |  |