# Cost Baseline and Cash Flow Plan — Skyhawk Solar + Storage Phase 1

Note on this document’s role as a worked example. This is the COMMITTED Cost Baseline and Cash Flow Plan for Skyhawk as it stood at the end of the Planning phase (ten weeks post-charter, post-Engineering 30% review), and as it evolved through Engineering 60% and into Construction. When the Budget Builder agent uses this as a worked example for a new project’s cost baseline, items shown with inline italic annotations — line-item dollar values dependent on detailed engineering, contingency allocations to specific risk categories, and the names of cost owners — should appear at the draft stage as [NEEDS PM REVIEW: <value>] rather than as the resolved values shown here. The final values shown reflect what the Northwood PM and Commercial Manager committed during the Planning sequence; a new project’s draft cost baseline would carry these in flagged form until detailed engineering supports the numbers.

## 1. Project context

- Project: Skyhawk Solar + Storage Phase 1 (NW-REN-2207)

- Client: Skyhawk Renewables LLC (IPP)

- Contract: Fixed-price, $68.0M

- Target Substantial Completion: 5 June, year+1

- Northwood PM: J. Okafor

- Commercial Manager: (at draft stage [NEEDS PM REVIEW: confirm Commercial Manager assignment]; assigned Week 4)

- Cost baseline date: Week 10 post-charter, post-30% Engineering

## 2. Cost baseline summary (P50)

The fixed-price contract value, target margin, approved cost budget, and contingency are committed in the charter §7. This section restates them and adds the operational structure used during execution.

| Line | $ million | Source / status |
| --- | --- | --- |
| Contract value | $68.0 | Charter §7 (committed) |
| Internal target margin | 8.8% | Charter §7 (committed) |
| Approved cost budget (P50) | $62.0 | Charter §7 (calculated as Contract value × (1 − margin); committed) |
| Northwood contingency | $2.5 | Charter §7 (at draft stage [NEEDS PM REVIEW: industry-standard contingency for this project class]; commercial team confirmed $2.5M at Week 2 review) |
| Total cost-to-Northwood envelope (P50 + contingency) | $64.5 | Calculated |
| Margin at full contingency consumption | $3.5 | Worst-case internal margin if entire contingency is drawn |
| LDs maximum exposure | $6.8 | Charter §7 (0.5%/week capped at 10%) |
| Retention held (peak) | $5.1 | Charter §7 (7.5% retention; this is the peak amount held before SC release of 50%) |

The Margin-at-full-contingency-consumption ($3.5M / 5.1%) is the internal floor below which the project would be flagged as commercially distressed. Below this floor, escalation to Sponsor is required.

## 3. Cost baseline by WBS branch

Decomposition aligned to the project’s WBS. Each Level-2 branch carries a P50 cost and a Northwood-internal confidence band derived from the 30% Engineering review.

| WBS branch | P50 cost ($M) | % of total | Confidence band | Source / status |
| --- | --- | --- | --- | --- |
| 1.0 Project Management | 3.1 | 5.0% | Tight | Northwood standard rate × 14-month duration |
| 2.0 Engineering & Design | 2.5 | 4.0% | Tight | Engineering staffing plan, 30% review confirmed |
| 3.0 Procurement — Solar PV modules (200 MW DC) | 18.6 | 30.0% | Tight | Three-bid procurement complete, vendor selected at Week 6 |
| 3.0 Procurement — Inverters | 4.3 | 7.0% | Tight | Three-bid procurement complete |
| 3.0 Procurement — BESS (100 MWh / 4-hour LFP) | 9.3 | 15.0% | Medium | (at draft stage [NEEDS PM REVIEW: BESS vendor selection — see Risk R2]; BESS vendor selected at Week 9, +/- 8% confidence band) |
| 3.0 Procurement — Substation & 230 kV equipment | 6.2 | 10.0% | Tight | Single-vendor substation package selected |
| 3.0 Procurement — Racking / trackers | 5.0 | 8.0% | Tight | Tracker vendor selected at Week 8 |
| 3.0 Procurement — BOS electrical (MV cabling, transformers) | 3.7 | 6.0% | Tight | Bulk procurement standard items |
| 4.0 Civil construction (foundations, grading, fencing) | 4.3 | 7.0% | Medium | Civil subcontract awarded at Week 12; T&M variation clause for desert-soil discovery |
| 5.0 Mechanical / electrical installation (subcontracts) | 3.7 | 6.0% | Medium | Two subcontract packages awarded at Week 14 |
| 6.0 Commissioning, performance testing, training | 1.0 | 1.6% | Tight | Northwood self-perform |
| 7.0 Project close (warranty admin, demobilisation) | 0.3 | 0.5% | Tight | Standard demobilisation cost |
| Total P50 cost budget | $62.0 | 100% |  | Matches charter §7 |
| Northwood contingency (separately tracked) | 2.5 | — | — | Charter §7 |

Branch confidence bands: “Tight” means the P50 value is within ±5% based on detailed engineering and vendor confirmation. “Medium” means ±10–15%, typically because vendor selection, subcontract award, or engineering completion lags. Branches without a tight band drive the contingency allocation in §4.

## 4. Contingency allocation reasoning

The $2.5M contingency is held by the PM as a discretionary fund. It is not pre-allocated to specific WBS branches at the baseline date, but the analytical allocation below shows the PM’s reasoning at planning:

| Risk source | Allocation ($k) | Tied to |
| --- | --- | --- |
| Utility interconnection studies delivered late (R1) | 400 | Schedule-driven cost; standby crew, expediting |
| BESS supply-chain disruption (R2) | 600 | Single-vendor concentration on a Medium-band procurement; covers re-qualification cost if required |
| Module degradation higher than design (R3) | 150 | Reserved for replacement modules within warranty if needed during commissioning |
| Weather events / monsoon-season productivity (R4) | 500 | Recovery overtime, sequence re-engineering during productive months |
| Local labour shortage / retention (R5) | 350 | Retention bonuses, partner with local trades for additional capacity |
| Unallocated reserve | 500 | PM discretionary; held for unanticipated discoveries |
| Total contingency | 2,500 | Charter §7 confirmed |

Of the $2.5M, $2.0M maps to the five charter §8 risks (R1–R5) and $0.5M is held as unallocated reserve. The PM may re-allocate within the envelope as risks materialise or close, but expansion beyond $2.5M requires Director approval per charter §11 governance.

## 5. Cash flow and payment milestone alignment

The contract is milestone-based with Net 30 payment terms. Invoiced revenue at each milestone is calculated from the milestone weights agreed in the contract; cumulative invoiced revenue must track ahead of cumulative cost-to-complete to keep the project cash-positive through to SC.

| Milestone | Target date | Invoiced (M)¦Cumulativeinvoiced(M) | Cumulative cost (M,projected)¦Networkingcapital(M) |  |  |
| --- | --- | --- | --- | --- | --- |
| Detailed Engineering 30% review | 30 June | 5.4 | 5.4 | 1.8 | 3.6 |
| Long-lead POs released (modules, inverters, BESS) | 15 August | — | 5.4 | 2.4 | 3.0 |
| Site mobilisation | 1 October | 8.2 | 13.6 | 6.5 | 7.1 |
| Mechanical Completion — PV array | 15 March, year+1 | 23.8 | 37.4 | 28.0 | 9.4 |
| BESS commissioned | 30 April, year+1 | 13.6 | 51.0 | 42.5 | 8.5 |
| Grid interconnection energisation | 1 May, year+1 | 5.4 | 56.4 | 49.0 | 7.4 |
| Substantial Completion | 5 June, year+1 | 8.6 | 65.0 | 58.0 | 7.0 |
| Retention release 1 (50% at SC) | 5 June, year+1 | 2.55 | 67.55 | 58.0 | 9.55 |
| Final warranty close (24 months later) | (warranty end) | 0.45 | 68.0 | 62.0 | 6.0 |

Net working capital is positive at every milestone. The lowest point is at Mechanical Completion BESS (Week 39 from contract effective), when committed but unbilled work is highest. (at draft stage [NEEDS PM REVIEW: confirm cumulative-cost projections against detailed cost-to-complete model; numbers shown here are Week 10 baseline projections]).

## 6. Cost reporting framework

### 6.1 Variance reporting cadence

- Weekly internal: cost-to-complete forecast vs P50 baseline, by WBS branch. Variance >2% on any branch flagged for review.

- Monthly client status: invoiced-vs-baseline at milestone level; no branch-level disclosure to client.

- Monthly portfolio: cumulative cost variance, contingency consumed-to-date, contingency-remaining vs. risks-remaining.

### 6.2 Earned value method

The project uses cost-plus-progress earned-value calculations:

- BCWP (Budgeted Cost of Work Performed) at each branch, calculated from progress percentages reported by the engineering, procurement, and construction leads.

- ACWP (Actual Cost of Work Performed) from invoiced and accrued cost data.

- BCWS (Budgeted Cost of Work Scheduled) from the schedule baseline.

- CPI (Cost Performance Index) = BCWP / ACWP. Target ≥ 1.00. CPI < 0.95 on any branch triggers PM-Director conversation; CPI < 0.90 triggers re-baseline review.

### 6.3 Re-baseline thresholds

- Single-branch overrun exceeding $200k OR exceeding 10% of branch P50, whichever is smaller: cost update, no re-baseline.

- Single-branch overrun exceeding $500k OR exceeding 20% of branch P50: re-baseline that branch with rationale; change-order if client-driven, internal-only if Northwood-driven.

- Total project cost overrun exceeding $1.5M (60% of contingency) OR margin projection dropping below 5.1% (full-contingency-consumed floor): portfolio escalation per charter §11 governance; immediate Sponsor brief.

Cost-baseline-integrity owner: J. Okafor (PM) with Commercial Manager support. Weekly cost reviews include the Construction Manager, Procurement Lead, and Engineering Lead.

## 7. Cost-linked risks

Five charter §8 risks have direct cost-impact channels. These are a subset of the charter §8 register, viewed through a cost lens; the register itself is not re-authored here.

| Risk (charter §8) | Cost impact channel | WBS branch affected | Expected cost range | Mitigation in budget |
| --- | --- | --- | --- | --- |
| R1 — Utility interconnection studies delivered late | Standby crew, expediting, schedule-cost crossover | Branch 5.0 / Commissioning windows | $0.2–0.6M | $400k contingency allocation (§4); schedule contingency in P80 (separate document) |
| R2 — BESS supply-chain disruption | Re-qualification or expediting; potential margin erosion | Branch 3.0 BESS | $0.3–0.9M | $600k contingency allocation; early PO, dual-source qualified, factory acceptance test |
| R3 — Module degradation higher than design | Replacement modules within warranty window | Branch 3.0 PV modules | $0.05–0.2M | $150k contingency; manufacturer warranty primary, contingency secondary |
| R4 — Weather events during construction | Recovery overtime, sequence re-engineering | Branches 4.0 Civil and 5.0 Mech/Elec | $0.3–0.7M | $500k contingency allocation; weather-window-aware sequencing |
| R5 — Local labour shortage | Retention bonuses, partner recruitment cost | Branches 4.0, 5.0 | $0.2–0.5M | $350k contingency; early recruitment, retention bonuses |

## 8. Conventions used

Five patterns this document follows, for traceability against the Northwood worked-example convention:

- Cost baseline as P50 plus separately-tracked contingency. The P50 budget ($62.0M) is the operational target. The $2.5M contingency is tracked separately. Combining them obscures both the operating-cost discipline and the risk-driven contingency reasoning.

- Decomposition by WBS branch with confidence bands. Each Level-2 WBS branch carries a P50 cost and a confidence band (Tight / Medium). Branches with Medium bands drive the contingency-allocation reasoning. The decomposition makes the cost baseline auditable against the WBS scope.

- Contingency allocation reasoned against the risk register. The $2.5M contingency is mapped to the five charter §8 risks (R1–R5) plus an unallocated reserve. This is the analytical view; the operational view is that the PM holds the $2.5M and may re-allocate. Re-allocation within the envelope is PM discretion; expansion beyond requires Director approval.

- Cash flow tied to milestone schedule with net working capital tracked at each milestone. The milestone-by-milestone cash projection is the basis for treasury planning and for catching the “low point” of net working capital before it becomes a problem.

- Re-baseline thresholds in dollars and percentages, not judgement calls. Single-branch and total-project thresholds are explicit. PM, Director, and Sponsor each have a clear escalation trigger.

## 9. Notes for downstream agents

- Status Reporter. Cost-variance reporting uses the WBS-branch table in §3 as the reference. The CPI ≥ 1.00 target and the 5.1% margin floor are the operational metrics to track week-on-week. Any branch reaching CPI < 0.95 or any movement toward the contingency consumption that leaves R-tied risk uncovered is a status-report material item.

- Risk Analyst. The five cost-linked risks in §7 are a filtered view of the charter §8 register. R2 (BESS supply chain) is the highest-impact cost-channel risk; the $600k allocation reflects the single-vendor concentration consequence. If new risks emerge during execution with cost impact, the contingency-allocation analysis in §4 updates with them.

- Variance Analyst. This document is the cost baseline against which variance is measured. Re-baseline events per §6.3 update this document; the change log at the head of the WBS dictionary records each event with date and rationale.

- Change Order Reviewer. Client-driven scope changes update the contract value (charter §7), the affected WBS branches (§3), and the cost-to-complete projection (§5 milestone table). The change-order analysis package always includes the marginal impact on the margin floor.