# Variance Analysis Report — Skyhawk Solar + Storage Phase 1 (Week 28 of 60)

Note on this document’s role as a worked example. This is a Variance Analysis Report for Skyhawk Solar at a mid-execution state — Week 28 of the 60-week project (about 47% into the construction phase). The report shows the variance discipline as it operates with real variance data to analyse: schedule and cost movement against baseline, root-cause analysis on material variances, contingency drawdown, and recovery action commitments. When the Variance Analyst agent uses this as a worked example for a new project, two adaptations apply. First, at a Week 0 baseline state, the agent produces the variance-measurement framework rather than a populated variance report — there is no variance to analyse yet, only the structure to be used going forward. Second, items shown with inline italic annotations — root-cause attributions where the evidence is partial, recovery-action target dates dependent on subcontractor commitment, and contingency drawdown rates that depend on future risk closure — would carry [NEEDS PM REVIEW] flags at draft stage. The Week 28 state shown reflects what the Skyhawk PM, Commercial Manager, and Schedule Engineer committed at that point in execution.

## 1. Project context and report period

- Project: Skyhawk Solar + Storage Phase 1 (NW-REN-2207)

- Client: Skyhawk Renewables LLC (IPP)

- Contract: Fixed-price, $68.0M; approved budget $62.0M; Northwood contingency $2.5M

- Northwood PM: J. Okafor

- Commercial Manager: D. Reeves

- Report period: Week 28 of 60 (mid-civil, BESS in FAT, long-lead module deliveries ongoing)

- Reporting cadence: Monthly client status (Week 28 is also the cadence-point for the Week-28 client status report)

- Variance baseline: Cost baseline at run-equivalent of Skyhawk’s 01e_budget_baseline.md; schedule baseline at Skyhawk’s planning-period schedule analysis

## 2. Executive summary — variance at a glance

| Metric | At Week 28 | Target / band | Status |
| --- | --- | --- | --- |
| Cost Performance Index (CPI) | 0.97 | ≥ 1.00 | Below target by 3% — explained, recovery in progress |
| Schedule Performance Index (SPI) | 0.95 | ≥ 1.00 | Below target by 5% — 2-week slip on civil critical path |
| Cumulative cost variance (CV) | −$0.6M | within ±2% of cumulative budget | At threshold |
| Cumulative schedule variance (SV) | −10 days against planned milestones | within ±14 days | Within tolerance |
| Contingency consumed-to-date | $0.7M of $2.5M (28%) | Track ahead of risk closure | Slightly ahead — explained |
| Contingency remaining vs unresolved risks | $1.8M against R1, R3, R4 still live | ≥ sum of expected exposures | Marginal — see §5 |
| Projected margin at SC (P50) | 8.2% | ≥ 8.8% target | Below target by 0.6%; above 5.1% distress floor |

One-sentence summary. Skyhawk is tracking 5% behind schedule and 3% over cost at Week 28 against an 8.8% target margin; the root causes are concentrated in two events (BESS vendor reselection in Week 18 and a two-week civil slip in Weeks 22–24), both of which have recovery plans active and contingency cover.

## 3. Schedule variance analysis

The schedule baseline (from 01_charter.md §6 milestones and the underlying construction schedule) anchors on five critical-path chains. Variance is reported by chain.

| Chain | Baseline activity | Planned end | Actual / forecast end | Variance | SPI (chain) |
| --- | --- | --- | --- | --- | --- |
| A — Detailed Engineering | Engineering 60% review | Week 11 | Week 11 | 0 days | 1.00 |
| B — Long-lead procurement | BESS PO release | Week 15 | Week 18 (at draft stage [NEEDS PM REVIEW: confirm against signed PO date]; PO released Week 18 to alternate vendor) | +21 days | 0.86 |
| B — Long-lead procurement | Modules and inverters delivered | Week 26 | Week 25 | −7 days (ahead) | 1.05 |
| C — Civil construction | Foundation pour 50% complete | Week 26 | Week 28 | +14 days | 0.93 |
| D — Mechanical erection | Not yet started | Week 32 planned start | Week 33 forecast start | +7 days | (forecast) |
| E — Commissioning and performance test | Not yet started | Week 52 planned start | Week 52 forecast start | 0 days | (forecast) |

Convergence assessment. Chain B BESS slip (Week 18 PO) has not yet propagated to Chain D mechanical erection because the BESS delivery slot is in Week 38 — sufficient buffer remains between PO release and required-on-site. Chain C civil slip (2 weeks against foundation milestone) is partially recoverable through subcontractor overtime in Weeks 29–32; the recovery plan targets re-alignment by Week 32. If neither recovery succeeds, Chain D start slips one week, which is recoverable within float to SC.

Net schedule position at Week 28. Critical path is currently behind by 14 days (Chain C civil). Float to SC remains positive at +20 days. The 30-day window between planned SC (Week 60) and the next external commitment (PPA energisation) is preserved.

## 4. Cost variance analysis

Cost variance is reported by WBS Level-2 branch, against the P50 baseline of $62.0M (from 01e_budget_baseline.md §3).

| WBS branch | P50 baseline (M)¦BCWPatWeek28(M) | ACWP at Week 28 (M)¦Variance(M) | CPI |  |  |
| --- | --- | --- | --- | --- | --- |
| 1.0 Project Management | 3.1 | 1.44 | 1.50 | −0.06 | 0.96 |
| 2.0 Engineering & Design | 2.5 | 2.40 | 2.35 | +0.05 | 1.02 |
| 3.0 Procurement — Modules | 18.6 | 18.6 | 18.0 | +0.6 | 1.03 |
| 3.0 Procurement — Inverters | 4.3 | 4.3 | 4.3 | 0 | 1.00 |
| 3.0 Procurement — BESS | 9.3 | 9.3 | 9.7 | −0.4 (at draft stage [NEEDS PM REVIEW: confirm against final PO with vendor-2]; finalised at $9.7M against budget $9.3M) | 0.96 |
| 3.0 Procurement — Substation | 6.2 | 5.0 | 5.0 | 0 | 1.00 |
| 3.0 Procurement — Racking | 5.0 | 5.0 | 5.0 | 0 | 1.00 |
| 3.0 Procurement — BOS electrical | 3.7 | 2.0 | 2.05 | −0.05 | 0.98 |
| 4.0 Civil construction | 4.3 | 2.0 | 2.3 | −0.3 | 0.87 |
| 5.0 Mechanical / electrical install | 3.7 | 0 | 0 | 0 | (n/a) |
| 6.0 Commissioning | 1.0 | 0 | 0 | 0 | (n/a) |
| 7.0 Project close | 0.3 | 0 | 0 | 0 | (n/a) |
| Project total — committed-and-spent | 62.0 | 50.04 | 50.20 | −0.16 | 0.997 |
| Project total — forward-projected to SC | 62.0 | 62.0 | 62.6 | −0.6 | 0.97 |

Largest variance items. Two branches drive the cumulative variance: BESS (−$0.4M, vendor reselection in Week 18) and Civil (−$0.3M, sub-grade conditions worse than design assumption discovered in Weeks 22–24). Module variance is favourable (+$0.6M, vendor competition stronger than bid assumption); this offset cushions but does not eliminate the unfavourable variances.

## 5. Contingency consumption status

The $2.5M contingency from charter §7 was analytically allocated against R1–R5 in 01e_budget_baseline.md §4. The Week 28 consumption status:

| Risk source | Allocation (k)¦Consumed−to−date(k) | Remaining ($k) | Risk status |  |
| --- | --- | --- | --- | --- |
| R1 — Utility interconnection late | 400 | 0 | 400 | Live — utility studies on track; first energisation test scheduled Week 50 |
| R2 — BESS supply disruption | 600 | 400 | 200 | Realised — vendor-2 reselection consumed; closing remainder if no further disruption |
| R3 — Module degradation | 150 | 0 | 150 | Live — modules in commissioning warranty window once erected |
| R4 — Weather / monsoon | 500 | 0 | 500 | Live — monsoon season Weeks 35–48; impact not yet materialised |
| R5 — Local labour shortage | 350 | 200 | 150 | Partially realised — civil slip Weeks 22–24 attributable in part to local labour availability; retention bonus drawdown $200k |
| Unallocated reserve | 500 | 100 | 400 | $100k drawn against sub-grade investigation cost not anticipated in any risk |
| Total | 2,500 | 700 | 1,800 |  |

Coverage analysis. Remaining contingency $1.8M against live risks projected exposure (R1 + R3 + R4 worst case ≈ $1.05M, R5 residual ≈ $150k, unallocated buffer $400k = total reserved exposure ≈ $1.6M). Margin of $200k on residual contingency vs residual risk exposure — tight but positive. If monsoon season produces material productivity loss (R4 realised), the $500k allocation may not cover, and the unallocated reserve becomes the secondary source. PM authority on additional contingency draw is exhausted at $500k beyond original allocation; Director approval required for any unanticipated event exceeding that.

## 6. Variance root cause analysis

Two material variances warrant detailed root-cause analysis at this report period.

### 6.1 BESS PO slip from Week 15 to Week 18 ($0.4M cost, 21 days schedule)

Trigger event. Original BESS vendor selected in proposal stage and confirmed at Week 6 review showed deteriorating financial-health indicators in Q3 vendor monitoring (Weeks 12–14): declining cash position, two analyst downgrades, supply-chain disruption reports from independent vendor’s prior projects.

Decision sequence. Week 14: Procurement Lead flagged the indicators; PM and Director reviewed in week-end meeting; decision made to suspend PO release pending alternate-vendor qualification. Week 15: alternate vendor (qualified in proposal but not preferred on price) engaged for accelerated commercial discussion. Week 17: alternate vendor commercial terms agreed at +$0.4M against original vendor’s proposed price. Week 18: PO released.

Root cause classification. External — vendor financial-health deterioration. Northwood acted prudently in not releasing the PO to a vendor at financial risk; the cost premium for the alternate is the consequence. R2 contingency allocation ($600k) was sized for this scenario at planning.

Lesson learned (provisional). Vendor financial-health monitoring frequency for sole-source long-lead items should increase from quarterly to monthly during the PO-release window; would have surfaced indicators 4–8 weeks earlier.

### 6.2 Civil schedule slip Weeks 22–24 ($0.3M cost, 14 days schedule)

Trigger event. Foundation excavation at the Solar Plot B (40% of array foundations) encountered sub-grade soil conditions softer than the geotechnical investigation indicated. Bearing capacity required additional excavation depth and structural fill in 18 of 80 foundation positions.

Decision sequence. Week 22: civil subcontractor flagged soft soil at first three positions. Week 23: PM ordered extended geotechnical investigation across Plot B; results showed broader subgrade weakness in the north-west quadrant. Week 24: revised foundation design with additional excavation depth approved; subcontractor mobilised additional equipment.

Root cause classification. External — sub-grade geotechnical variance from investigation. Investigation was per Northwood standard for projects of this size; the affected quadrant did not feature in the original sampling grid which was concentrated in higher-risk topographic areas. R5 contingency allocation (local labour) covers part of the cost; the unallocated reserve covers the geotechnical investigation cost ($100k) that was not anticipated in any specific risk.

Lesson learned (provisional). For solar projects on terrain with variable soil profiles, geotechnical investigation grid density should be uniform across the footprint, not concentrated in topographically-high-risk areas. Standard sampling pattern updated.

## 7. Recovery actions

Four recovery actions are committed for the period Weeks 29–40.

| Action | Owner | Target close | Linked variance | Status |
| --- | --- | --- | --- | --- |
| Civil subcontractor overtime Weeks 29–32 to recover 14-day foundation slip | Construction Manager | Week 32 | §6.2 | In progress |
| BESS factory acceptance test in Week 38 with on-site expediter from Week 35 | Procurement Lead | Week 38 | §6.1 | Planned |
| Pre-monsoon work-front loading: complete erosion-control installation by Week 34 to maximise productive monsoon-season days | Construction Manager | Week 34 | R4 forward | In progress |
| Increase vendor financial-health monitoring on all remaining long-lead POs from quarterly to monthly through end of construction | Procurement Lead | Standing through SC | §6.1 lesson | Active |

Recovery cost projection. Civil subcontractor overtime estimated $80k (within existing branch contingency, not contingency drawdown). Pre-monsoon loading is sequence-only, no incremental cost. Vendor monitoring is process change, no incremental cost. BESS expediter cost ($30k) absorbed in 3.0 Procurement branch.

## 8. Outlook to next reporting period (Weeks 29–32)

Expected variance evolution. SPI projected to improve from 0.95 to 0.97 by Week 32 if civil recovery succeeds as planned; CPI projected to stay at 0.97 (no new material variances anticipated). Contingency consumption projected to add $100k against R5 (retention bonus continuation) and $0 against other risks if monsoon delays. Monsoon season begins Week 35; first material R4 exposure window opens Week 36.

Watch items. - Civil overtime delivery (does the 14-day recovery materialise by Week 32?) - BESS vendor-2 performance through FAT (does the PO premium hold or grow?) - Module deliveries continuing on cadence (does the favourable variance persist?) - Erosion-control completion by Week 34 (does the pre-monsoon loading deliver as planned?)

Re-baseline trigger assessment. No current trigger exceeded. The 5.1% margin floor (full contingency consumed) remains uncrossed at projected 8.2%. Single-branch overrun thresholds (BESS at −$0.4M against branch limit −$1.0M; Civil at −$0.3M against branch limit −$0.5M) remain below re-baseline triggers. Total-project overrun at −$0.6M against total threshold −$1.5M (60% contingency consumed) remains below threshold.

## 9. Conventions used

Five patterns this document follows, for traceability against the Northwood worked-example convention:

- EVM as the variance backbone. CPI and SPI are the headline metrics; CV and SV are the dollar / day measurements. The metrics inherit their formulas from PMBOK Earned Value Method conventions. Numbers without a unit are absolute dollars or days; ratios are decimal.

- Variance reported by WBS Level-2 branch and by critical-path chain. The same variance appears once in each view — once by branch (cost lens) and once by chain (schedule lens). Cross-references between the two views are explicit where they describe the same underlying event.

- Root-cause analysis disciplined and evidence-bearing. Root causes are classified (Internal Northwood, External vendor, External client, External regulatory, External natural/site, Methodological). Evidence is cited (vendor monitoring data, geotechnical reports, subcontractor flags). Speculation is flagged with inline italic annotations where the evidence is partial.

- Recovery actions named, owned, dated, and cost-projected. Every recovery action has a single owner, a target close date, a linked variance section, and an estimated cost or scope-only classification. Aspirational recovery without commitment is not recorded as an action.

- Re-baseline trigger assessment included at every reporting period. Even when no triggers are crossed (as here at Week 28), the assessment is explicit: which thresholds remain how far from triggers. This is the discipline that gives the PM, Director, and Sponsor pre-warning before re-baseline events arrive.

## 10. Notes for downstream agents

- Status Reporter. The Executive Summary (§2) and the Outlook (§8) feed the monthly client status report. The Cost variance (§4) and Schedule variance (§3) feed the monthly portfolio dashboard. Root-cause analyses (§6) are summarised for the Sponsor brief; full detail is internal-only unless the variance event has been disclosed to the client.

- Change Order Reviewer. Variance events with client-driven causation flow into the change-order log. None of the Week 28 variances are client-driven; if a future variance traces to a client-instructed scope or sequence change, the change-order package is the recovery vehicle.

- Risk Analyst. Realised risks (R2 BESS, R5 partially) update the risk register status from “Live” to “Realised / Materialised.” The risk register’s standalone document should be updated in the same reporting cycle to maintain consistency between the issue log, the variance analysis, and the risk register.

- Issue Logger. Variance events that originated as upstream open items (e.g., R2 BESS vendor selection was originally I-002-equivalent on Skyhawk’s Week 0 baseline) close on the issue log with a Linked-variance reference back to this document. The issue log’s closed-state lifecycle entry cites the variance analysis where the operational closure was achieved.