# Weekly Status — Skyhawk Solar + Storage Phase 1

Project: NW-REN-2207 Reporting period: Week 44 of construction (ending Sunday) PM: J. Okafor Status (overall): Amber — Interconnection studies late, recovery plan in place

## Headline

Utility interconnection studies confirmed Friday as 3 weeks late vs PPA-implied date, threatening grid energisation milestone of 1 May. Recovery plan agreed with utility coordinator: parallelise final commissioning checks, add a second commissioning crew weeks 50–52. Substantial Completion date holds.

## Progress

- Engineering: 100% complete.

- Procurement: all POs closed. BESS containers delivered; FATs all passed.

- Construction: PV mechanical completion 92%; substation 100%; MV collection 95%.

- Commissioning: PV string commissioning 60%; BESS commissioning ready to commence Week 46.

## Schedule

- Variance to plan: -1 week against current baseline.

- Critical path: Grid interconnection. Recovery plan absorbs 2 of 3 weeks of slip.

- Forecast completion: 5 June (on baseline).

## Cost and commercial

- Cost-to-date vs plan: -$200k under spend.

- Forecast at completion: +$180k overrun (overtime for second commissioning crew).

- Margin trajectory: holding at 8.8% (bid 8.8%).

- Active change orders: CO-02 (revised fence specification, $45k); CO-03 (additional access road, $230k, in negotiation).

- Claims: considering schedule-impact letter on utility interconnection delay.

## Risks and issues

- Triggered: R-001 (utility interconnection delay). Recovery plan executing.

- New: R-009 — Module shipment to be physically inspected pre-installation following industry advisory on a specific manufacturing batch. Inspection scheduled Week 45.

## Safety / quality / environment

- Zero LTIs. 2 first-aid cases this period. One environmental near-miss (minor fuel spill from a sub-contractor truck, fully contained, reported per protocol).

## Look-ahead

- BESS commissioning commences Week 46.

- Utility energisation walkthrough, Week 48.

- Module batch inspection report, Week 45.

- Client visit, Week 47.

## Asks

- Director to support escalation with utility GM if Week 46 milestone slips. Owner: L. Chen.

- Sponsor approval of CO-03 once client signs ($230k revenue, ~10% margin). Owner: VP Renewables.