# Risk Register — Skyhawk Solar + Storage Phase 1

Project ID: NW-REN-2207 Status snapshot: End of project. All risks closed.

| ID | Category | Description | Probability | Impact | Score | Response | Owner | Trigger | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-001 | Regulatory | Utility interconnection studies delivered late, delaying energisation date and PPA commencement. | M | H | 6 | Mitigate — engage utility coordinator Day 1, escalation path via PPA terms | Project Manager | Utility confirms slip > 2 weeks at any review | Closed (Triggered Wk 43; recovery plan executed; SC on time) |
| R-002 | Schedule | BESS supply-chain disruption from sole-source OEM. | M | H | 6 | Mitigate — early PO, dual-source qualification, FAT before shipment | Procurement Manager | OEM signals delay > 4 weeks | Closed (FATs passed; delivery on time) |
| R-003 | Technical | Module degradation in operation higher than design assumption. | L | M | 2 | Accept — 25-year manufacturer warranty, performance bond | Engineering Lead | Performance test results > 1% off spec | Closed (passed performance test in margin) |
| R-004 | Schedule | Monsoon season weather impacts civil works productivity. | M | M | 4 | Mitigate — front-load weather-sensitive work, daily weather review | Construction Manager | More than 5 lost-day events in any month | Closed (4 lost-day events total; productivity tracked plan) |
| R-005 | People | Regional labour shortage from competing construction boom. | M | M | 4 | Mitigate — early recruitment, retention bonuses, partner with local trades | HR / Construction Manager | Open positions remain > 4 weeks past target | Closed (workforce stabilised by Week 8) |
| R-006 | External | Land access dispute with neighbouring landowner. | L | M | 2 | Accept — legal review, client responsibility | Client | Notice from landowner | Closed (no dispute arose) |
| R-007 | Safety / HSE | High-temperature exposure for construction workforce in summer months. | M | M | 4 | Mitigate — adjusted shift patterns, hydration stations, heat-stress monitoring | HSE Lead | Any heat-stress incident | Closed (zero heat-stress incidents; 2 near-misses fed back to programme) |
| R-008 | Commercial | Currency exposure on inverter and BESS POs (USD-denominated; no exposure expected). | L | L | 1 | Accept — USD-denominated POs | Procurement Manager | Vendor changes pricing currency | Closed (no exposure) |
| R-009 | Technical | Module manufacturing batch advisory (industry-wide) requires inspection of received units. | M | L | 2 | Mitigate — physical inspection of all batches before installation | QA Lead | Industry advisory issued | Closed (inspection passed; no rework) |
| R-010 | External | Wildfire risk to project site during construction. | L | H | 3 | Mitigate — fire breaks, hot-work permits, on-site water reserves | HSE Lead | Regional fire-danger index > “Very High” | Closed (one fire-watch standdown of 2 days; no incident) |

## Lessons logged

- Utility interconnection is a perennial schedule risk. Recurred from Riverside (where it was different — state regulator inspection — but same pattern). PMO standard should be earliest possible engagement with all external dependency owners.

- Dual-sourcing critical equipment paid off again. Even though primary source delivered, the qualified secondary gave us pricing leverage and accelerated-delivery options if needed.

- Weather window management is a Day-1 discipline, not a recovery technique. Two of the four monsoon lost-day events were avoidable with better look-ahead — fed back into the firm’s weather-management standard.