# Project Charter — Ironvale Smelter Modernisation

## 1. Project identification

- Project name: Ironvale Smelter Modernisation

- Project ID: NW-IND-2110

- Client: Ironvale Metals Group

- Contract type: T&M with cap ($30M cap)

- Contract value: $26.5 million (working value at Award)

- Effective date: 14 August

- Target Mechanical Completion: 30 June, year+1

- Sponsor (Northwood): VP Industrial

- Project Director: S. Friedman

- Project Manager: P. Beaumont

## 2. Overview

Modernisation of an operating secondary aluminium smelter to extend plant life by 20 years and bring emissions performance within the latest state air-quality limits. Northwood replaces two of the three furnace lines, upgrades the SCADA and instrumentation system end-to-end, installs new baghouse and scrubber for environmental control, and ties the new lines into the existing crucible casting bays.

## 3. Objectives

- Replace Furnace Lines A and B with new technology, verified through 14-day production performance test, by 30 June year+1.

- Achieve emissions compliance with state Air Quality Rule 27 (effective immediately at restart) verified during commissioning.

- Maintain client production output on the unaffected Furnace Line C throughout construction (no shutdown of C beyond planned tie-in week).

- Deliver at or above 10% margin with cost variance within ±5% (T&M cap rules).

- Zero lost-time injuries.

## 4. Scope

### 4.1 In scope

- Detailed design of furnace lines A and B, SCADA, baghouse, scrubber.

- Procurement of furnaces, baghouse modules, scrubber, motor control centres, instrumentation, control system hardware.

- Demolition of existing Furnace Lines A and B.

- Construction and installation of new lines, environmental controls, SCADA upgrade.

- Tie-ins to existing crucible bays and ancillary services.

- Commissioning, performance testing, operator training, as-builts.

- 12-month warranty (shorter than standard due to T&M structure).

### 4.2 Out of scope

- Furnace Line C (not part of this scope).

- Casting bay equipment.

- Site civil works beyond the furnace bay perimeter.

- Permits (client).

## 5. Key stakeholders

| Role | Name | Organisation | Responsibility |
| --- | --- | --- | --- |
| Sponsor | VP Industrial | Northwood | Internal accountability |
| Project Director | S. Friedman | Northwood | Commercial outcome |
| PM | P. Beaumont | Northwood | Day-to-day delivery |
| Client Plant Engineer | T. Hartnett | Ironvale Metals | Embedded with Northwood team |
| Client Operations Manager | (Various) | Ironvale Metals | Production interface |
| State Air Regulator | (Various) | State Environmental | Permit, sign-off |

## 6. Schedule and milestones

| Milestone | Target date | Payment milestone? |
| --- | --- | --- |
| Engineering 60% review | 15 December | Yes |
| Long-lead furnace POs released | 15 January year+1 | No |
| Demolition complete | 28 February year+1 | Yes |
| Furnace Line A mechanical complete | 15 April year+1 | Yes |
| Furnace Line B mechanical complete | 30 May year+1 | Yes |
| Environmental controls commissioned | 10 June year+1 | Yes |
| Plant shutdown for tie-in | 15–22 June year+1 | No |
| Mechanical Completion | 30 June year+1 | Yes |

## 7. Commercial baseline

- Working value: $26.5M; cap $30.0M.

- Internal target margin: 10%.

- Approved budget (cost): $23.85M (against working value).

- Contingency: Embedded in cap differential.

- LDs: Limited; daily rate $25k capped at $1M.

- Retention: 5%.

- Payment terms: Monthly progress billing, Net 30.

## 8. Risks (top 5)

| Risk | Category | Probability | Impact | Response |
| --- | --- | --- | --- | --- |
| Latent defects in 35-year-old facility surface during demolition | Technical | M | M | Mitigate — pre-demolition surveys; T&M structure absorbs limited variation; client cost-share above threshold |
| Plant shutdown window for tie-in exceeds 7 days | Schedule | L | H | Mitigate — extensive dry-runs, parallel work fronts, full pre-assembly off-site |
| State regulator permit conditions tighten during project | Regulatory | L | M | Accept — regular liaison, change-order vehicle if conditions change |
| Furnace OEM delivery delay | Schedule | M | M | Mitigate — early PO, expediting, qualified alternative |
| Production interruption on Furnace Line C during construction | Commercial | L | H | Avoid — physical isolation, dedicated client liaison, daily coordination |

## 9. Assumptions

- Existing site documentation reflects current as-installed conditions (Ironvale digitised records 2 years ago).

- Client provides agreed 7-day shutdown window in June year+1.

- Permits remain valid through Mechanical Completion.

## 10. Constraints

- Furnace Line C must remain operational throughout construction except during the agreed shutdown window.

- State Air Quality Rule 27 effective immediately at restart of Lines A and B.

## 11. Governance

- Reporting cadence: weekly internal, biweekly client, monthly portfolio.

- Decision rights: PM up to $40k, Director up to $400k, Sponsor above.

- Change orders: T&M contract with cap; variations through formal change-order with client cost-share at thresholds defined in contract.

- Escalation: PM → Director → Sponsor.

## 12. Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Sponsor | VP Industrial | (signed) | 10 August |
| Project Director | S. Friedman | (signed) | 10 August |
| Project Manager | P. Beaumont | (signed) | 14 August |