# Weekly Status — Ironvale Smelter Modernisation

Project: NW-IND-2110 Reporting period: Week 32 of construction (ending Sunday) PM: P. Beaumont Status (overall): Green — On schedule, on budget, latent defect surfaced and contained

## Headline

Furnace Line A mechanical completion achieved Friday, two days ahead of plan. One latent defect discovered during demolition (cracked structural bracket in support frame) has been engineered around without schedule impact; client cost-share invoked under contract terms.

## Progress

- Engineering: 100%.

- Procurement: Line A 100%; Line B equipment in transit, due Week 34.

- Construction: Line A 100% mechanical; Line B 64% mechanical.

- Commissioning: Line A commissioning to commence Week 34.

## Schedule

- Variance to plan: +2 days ahead of baseline.

- Critical path: Line B mechanical completion → tie-in week.

- Forecast completion: 30 June year+1 (on baseline).

## Cost and commercial

- Cost-to-date vs plan: -$60k under spend on T&M.

- Forecast at completion: $26.8M (working value), well within cap.

- Margin trajectory: holding at 10%.

- Active change orders: CO-03 (latent defect remediation, $48k, 70/30 client cost-share per contract).

## Risks and issues

- New: R-008 — Cracked bracket in Line A support frame found during demolition. Engineered around, structural calc reviewed by client. No further action.

- Watching: R-002 (Line B furnace delivery). On schedule for Week 34 dock.

## Safety / quality / environment

- Zero LTIs to date. 1 first-aid case this period. Air-quality monitoring during demolition consistently below action levels.

## Look-ahead

- Line A commissioning begins Week 34.

- Line B furnace OEM delivery to site, Week 34.

- Client mid-project review meeting, Week 35.

## Asks

- Director sign-off on CO-03 once client countersigns. Owner: S. Friedman.

- Confirm shutdown window scheduling with client Operations Manager, Week 33. Owner: PM.