# Risk Register — Ironvale Smelter Modernisation

Project ID: NW-IND-2110 Status snapshot: End of project. All risks closed.

| ID | Category | Description | Probability | Impact | Score | Response | Owner | Trigger | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-001 | Technical | Latent defects in 35-year-old facility may surface during demolition, requiring rework. | M | M | 4 | Mitigate — pre-demolition surveys, T&M structure absorbs limited variation, client cost-share above threshold | Engineering Lead | Any structural or process discovery not in record drawings | Closed (R-008 invoked for cracked bracket; one further item absorbed) |
| R-002 | Schedule | Furnace OEM delivery delay risk on Lines A and B. | M | M | 4 | Mitigate — early PO, expediting, qualified alternative OEM | Procurement Manager | OEM signals slip > 3 weeks | Closed (both deliveries on time) |
| R-003 | Schedule | Plant shutdown window for final tie-in exceeds 7 days. | L | H | 3 | Mitigate — dry runs, parallel work fronts, off-site pre-assembly | Construction Manager | Day-by-day tie-in plan slips > 4 hours at any review | Closed (tie-in completed in 6 days, 1 day ahead) |
| R-004 | Regulatory | State Air Quality Rule 27 conditions tighten during project. | L | M | 2 | Accept — regular liaison, change-order vehicle | Project Manager | Regulator publishes amended conditions | Closed (no change) |
| R-005 | Commercial | Production interruption on Furnace Line C during construction. | L | H | 3 | Avoid — physical isolation, dedicated client liaison, daily coordination | PM + Client Operations | Any unplanned C-line stoppage tied to construction | Closed (zero unplanned C-line interruptions) |
| R-006 | Safety / HSE | Hot-work exposure during demolition of operating-adjacent equipment. | M | M | 4 | Mitigate — hot-work permit system, dedicated fire-watch, daily JSA | HSE Lead | Any hot-work permit non-compliance audit finding | Closed (one minor finding addressed; zero incidents) |
| R-007 | Technical | SCADA migration may introduce control upsets on Line C during cutover. | L | H | 3 | Mitigate — parallel running, rollback plan, staged cutover with manual fallback | I&C Lead | Any control variance during parallel-run testing | Closed (clean cutover) |
| R-008 | Technical | Cracked structural bracket in Line A support frame discovered during demolition. | (Triggered) | M | — | Mitigate — engineered around, structural recalc, client cost-share | Engineering Lead | Discovery during demolition | Closed (engineered, CO-03 executed) |
| R-009 | People | Client plant engineer reassignment would lose embedded coordination. | L | M | 2 | Accept — succession briefed via PM; project knowledge documented | Project Manager | Client communicates reassignment | Closed (no reassignment) |

## Lessons logged

- Embedded client SME is a multiplier. T. Hartnett’s daily presence accelerated decisions and reduced rework. Northwood should ask for this on every modernisation project where the client has the relevant expertise.

- T&M with a cap is the right contract structure for projects with high latent-condition risk. Aligns incentives, allows scope to evolve in Engineering, contains client exposure. Should be a default consideration on facility-modernisation work.

- A full plant shutdown is sometimes the cheapest path. The client’s willingness to give us a full week was the single largest schedule contributor. Future modernisation bids should make the cost-benefit case for full shutdown openly with the client.